CHATCO BACKEND SPRINT ROADMAP

Backend-Only Sprint Plan  •  June 16 – August 15, 2025

Laravel + Supabase  |  Sanctum Auth  |  GCash Direct QR  |  GPS + Hail System

## Executive Summary

This roadmap covers 9 backend-only sprints from June 16 to August 15, 2025, targeting production readiness for the Chatco jeepney tracking system. The frontend (Next.js) is already implemented; this plan exclusively addresses the Laravel backend that the frontend expects to connect to.

Key architectural decisions confirmed throughout all sprints:

- Wallet system is fully and permanently removed — no internal balance, no top-up, no ledger

- GCash QR is direct external payment via PayMongo only — no internal money movement

- All jeepney units are visible to commuters at all times — no distance filter on visibility

- 1KM hail restriction is enforced server-side only — frontend is display-only

- Backend is the single source of truth — frontend never bypasses backend validation

## Backend Architecture at a Glance

| Layer | Implementation |
| --- | --- |
| API Framework | Laravel 11 (PHP 8.2+) |
| Database | Supabase (PostgreSQL) via Eloquent ORM |
| Authentication | Laravel Sanctum — SPA cookie-based + token fallback |
| Roles | ADMIN ¦ CONDUCTOR ¦ COMMUTER — enforced by middleware |
| GPS | POST /api/conductor/location → vehicle_locations table (upsert) |
| Hail Radius | Haversine server-side in HailService — 1000m hard limit |
| Payment | GCash via PayMongo API — no internal wallet or balance |
| Real-time | 5s polling (MVP); Laravel Echo/Pusher optional upgrade |

## Weekly Sprint Breakdown

WEEK 1    June 16 – June 22, 2025

Sprint Goal: Laravel project bootstrap — auth skeleton, DB schema, Sanctum, role middleware

🛣️  API & Route Work

- Install Laravel 11 + configure .env (DB, CORS, Sanctum, mail)

- Register all route groups: api/auth, api/commuter, api/conductor, api/admin, api/payments, api/qr

- Return 501 Not Implemented stubs for all non-auth endpoints (prevents silent failures)

- Standardize all API responses: { success, data, message, errors, meta } format

🔐  Auth & Security

- Install & configure Laravel Sanctum (cookie-based, SPA)

- Implement POST /api/auth/login

- Validate email + password

- Return Sanctum token or set httpOnly session cookie

- Embed role claim in response: { id, email, role }

- Implement POST /api/auth/logout (revoke token)

- Implement GET /api/user (return authenticated user + role)

- Create role middleware: EnsureRole::class (admin, conductor, commuter)

- Protect all non-auth route groups with auth:sanctum + role middleware

⚙️  Core System Logic

- No business logic this week — focus on foundation only

- Confirm roles enum in DB: ADMIN, CONDUCTOR, COMMUTER

🗃️  Database / Laravel Structure

- Create migrations: users, conductors, commuters, vehicles, shifts, transactions, hails, remittances, announcements, lost_items, feedback

- Seed: 1 admin, 2 conductors, 3 commuters, 3 vehicles

- Create base models with $fillable, $hidden, $casts

- No wallet table — confirm it does not exist in any migration

📡  Real-time / GPS

- No GPS work this week

- Create placeholder route: POST /api/conductor/location (returns 501)

🧹  Code Quality

- Folder structure: app/Http/Controllers/{Auth,Commuter,Conductor,Admin,Payment}, app/Services/, app/Http/Middleware/

- No business logic inside controllers — controllers call services only

✅  Validation Checklist

- POST /api/auth/login returns token + role

- GET /api/user returns user behind auth:sanctum

- Non-auth routes return 401 when unauthenticated

- Role middleware blocks wrong-role access (test: commuter hitting /api/admin)

- No wallet table in DB schema

- All routes registered and returning 501 stubs (not 404)

WEEK 2    June 23 – June 29, 2025

Sprint Goal: Conductor shift + GPS location system — production-grade shift lifecycle

🛣️  API & Route Work

- POST /api/conductor/shifts/start — create shift, link to conductor + vehicle

- POST /api/conductor/shifts/{id}/end — close shift, compute duration

- GET /api/conductor/shifts/active — return active shift for authenticated conductor

- GET /api/conductor/shift-logs — paginated shift history

- POST /api/conductor/location — accept { lat, lng, speed, heading } GPS payload

- GET /api/vehicles/locations — return all active vehicle locations (commuter-facing)

🔐  Auth & Security

- All conductor routes behind auth:sanctum + role:conductor middleware

- Conductor can only access their own shifts (scope by conductor_id = auth()->id())

- Reject duplicate active shifts: one conductor = one active shift max

⚙️  Core System Logic

- Shift states: pending → active → ended (enforce server-side transitions)

- GPS update: store latest lat/lng per vehicle in vehicle_locations table (upsert by vehicle_id)

- Vehicles table: track active_shift_id FK for real-time status

- Capacity status: Available / Standing / Full — conductor updates via API, never inferred by frontend

🗃️  Database / Laravel Structure

- Migration: vehicle_locations (vehicle_id, conductor_id, lat, lng, speed, heading, capacity_status, updated_at)

- Migration: shifts (id, conductor_id, vehicle_id, started_at, ended_at, status)

- ShiftService: startShift(), endShift(), getActiveShift()

- LocationService: updateLocation(), getAllActiveLocations()

📡  Real-time / GPS

- POST /api/conductor/location: validate lat (-90 to 90), lng (-180 to 180), required fields

- Upsert vehicle_locations on every POST — always latest position only

- GET /api/vehicles/locations: return all vehicles with lat, lng, capacity_status, plate_number

- Frontend polls GET /api/vehicles/locations every 5s (no WebSocket needed this sprint)

🧹  Code Quality

- ShiftController → delegates entirely to ShiftService

- LocationController → delegates entirely to LocationService

- No raw DB queries in controllers

✅  Validation Checklist

- Conductor can start exactly one active shift

- Second start attempt returns 409 Conflict

- GPS POST updates vehicle_locations (verify in DB)

- GET /api/vehicles/locations returns all vehicles regardless of distance

- Commuter role cannot POST /api/conductor/location (403 expected)

- Shift end sets ended_at timestamp

WEEK 3    June 30 – July 6, 2025

Sprint Goal: Hail system with server-enforced 1KM radius — backend is the sole gatekeeper

🛣️  API & Route Work

- POST /api/commuter/hail — create hail request

- DELETE /api/commuter/hail/{id} — cancel hail

- GET /api/conductor/hails — conductor sees pending hails for their vehicle

- POST /api/conductor/hails/{id}/accept — conductor accepts hail

- POST /api/conductor/hails/{id}/reject — conductor rejects hail

🔐  Auth & Security

- Hail POST requires auth:sanctum + role:commuter

- Conductor hail actions require auth:sanctum + role:conductor

- Commuter can only cancel their own hail

⚙️  Core System Logic

- 1KM Radius Enforcement (SERVER-SIDE ONLY)

- On POST /api/commuter/hail: receive { vehicle_id, commuter_lat, commuter_lng }

- Fetch latest vehicle lat/lng from vehicle_locations

- Compute Haversine distance server-side

- If distance > 1000m → return 422 { error: 'outside_radius', distance_m: N }

- If distance <= 1000m → create hail record

- Frontend distance check is DISPLAY-ONLY and must never be the sole validator

- Hail states: pending → accepted | rejected | cancelled | expired

- Hail expiry: auto-expire pending hails after 3 minutes (queue job or GPS poll)

- Vehicle visibility: GET /api/vehicles/locations returns ALL vehicles — no radius filter here

🗃️  Database / Laravel Structure

- Migration: hails (id, commuter_id, vehicle_id, conductor_id, commuter_lat, commuter_lng, distance_m, status, created_at, expires_at)

- HailService: createHail(), cancelHail(), acceptHail(), rejectHail(), expireStaleHails()

- HailRequest FormRequest: validate lat/lng ranges, vehicle_id exists and is active

📡  Real-time / GPS

- Hail creation triggers distance validation against live vehicle_locations

- Conductor sees hails via GET /api/conductor/hails — scoped to their vehicle_id

- Consider: scheduled job every 60s to expire stale hails (Laravel scheduler)

🧹  Code Quality

- HailController is thin — all logic in HailService

- Haversine function in app/Helpers/GeoHelper.php (reusable, testable)

- Remove any 1KM logic from frontend API route stubs — it must only live in backend

✅  Validation Checklist

- Hail at 0.5km succeeds (201 Created)

- Hail at 1.5km fails (422, error: outside_radius)

- Admin/conductor cannot POST /api/commuter/hail (403)

- GET /api/vehicles/locations still returns ALL vehicles even if commuter is far

- Conductor can accept/reject only hails for their vehicle

- Cancelled hail status = cancelled in DB

WEEK 4    July 7 – July 13, 2025

Sprint Goal: Transaction system + GCash QR payment flow (no wallet, direct payment only)

🛣️  API & Route Work

- POST /api/conductor/transactions — record a fare transaction (cash or GCash)

- GET /api/conductor/transactions?shift_id={id} — list transactions for a shift

- POST /api/gcash/charge — initiate GCash direct payment (proxies to PayMongo)

- GET /api/payments/verify?id={id} — verify payment status

- POST /api/payments/webhook — PayMongo webhook for async payment confirmation

- GET /api/commuter/payments — commuter payment history

🔐  Auth & Security

- POST /api/gcash/charge requires auth:sanctum (conductor role)

- Webhook endpoint: verify PayMongo signature header (prevent spoofed callbacks)

- Commuter can only see their own payment history

- No admin can create transactions directly

⚙️  Core System Logic

- GCash Payment Flow (Direct, No Wallet)

- Conductor selects GCash for a commuter fare

- Backend calls PayMongo: POST /payment_intents with amount in centavos

- Return QR source URL to frontend for display

- Commuter scans QR in GCash app

- PayMongo calls /api/payments/webhook on completion

- Backend updates transaction status to paid

- NO internal balance, NO wallet credit, NO stored funds — payment only

- Cash transactions: record immediately, status = paid, no external API

- Transaction record must link: shift_id, conductor_id, commuter_id (if known), fare_amount, payment_method, status

🗃️  Database / Laravel Structure

- Migration: transactions (id, shift_id, conductor_id, commuter_id?, amount, payment_method, status, paymongo_id?, paid_at, created_at)

- Confirm: no wallet_balance column on any table, no wallet_transactions table

- TransactionService: createTransaction(), verifyGCashPayment(), handleWebhook()

- PaymentService: createPaymentIntent(), verifyIntent() — wraps PayMongo API

📡  Real-time / GPS

- Webhook: when payment confirmed → update transaction.status = paid + transaction.paid_at

- Frontend polls GET /api/payments/verify every 3s after QR display (fallback if webhook delayed)

🧹  Code Quality

- PayMongo API key stored in .env only — never in code

- PaymentService handles all external calls — TransactionController never calls PayMongo directly

- Webhook handler validates signature before processing any data

✅  Validation Checklist

- Cash transaction records correctly in DB

- GCash flow: POST /api/gcash/charge returns QR data without creating wallet

- Webhook updates transaction status to paid

- Commuter payment history shows transactions

- No wallet table or wallet balance column in DB (confirm via schema inspection)

- PayMongo secret key is NOT hardcoded (check .env)

WEEK 5    July 14 – July 20, 2025

Sprint Goal: Commuter profile, admin CRUD, remittance, and role-scoped data access

🛣️  API & Route Work

- GET/PUT /api/commuter/profile

- POST /api/commuter/change-password

- GET /api/conductor/remittances + POST /api/conductor/remittances

- GET /api/admin/users — paginated, filterable by role

- GET/PUT/DELETE /api/admin/users/{id}

- GET /api/admin/vehicles + POST + PUT/DELETE

- GET /api/admin/monitoring — live fleet data

- GET /api/admin/analytics — aggregated metrics

🔐  Auth & Security

- Commuter profile: user can only modify their own data

- Admin endpoints: all behind role:admin middleware

- Admin cannot impersonate users via API (no user-switching endpoint)

- Password change: validate current_password before allowing update

⚙️  Core System Logic

- Remittance: conductor submits daily collection amount at end of shift

- Remittance links to shift_id — one remittance per shift

- Admin monitoring: aggregate from vehicle_locations + active shifts in real-time

- Analytics: aggregate transactions by date, route, payment_method (no wallet metrics)

🗃️  Database / Laravel Structure

- Migration: remittances (id, conductor_id, shift_id, total_collected, remitted_amount, created_at)

- Admin views use DB aggregates — no fake/static data

- CommuterService, ConductorService, AdminService separation

- All services return typed data — controllers just format responses

📡  Real-time / GPS

- GET /api/admin/monitoring: real-time vehicle positions from vehicle_locations

- Admin monitoring refreshes every 5s (same polling mechanism as commuter map)

🧹  Code Quality

- Remove any static/hardcoded admin data from backend stubs

- Ensure commuter endpoints never leak conductor/admin data

- Clean up any duplicated profile logic between AuthController and CommuterController

✅  Validation Checklist

- Commuter cannot access /api/admin endpoints (403)

- Admin can list, update, delete users

- Remittance links to correct shift_id

- Profile update persists to DB

- Analytics endpoint returns real aggregated data, not mocked values

WEEK 6    July 21 – July 27, 2025

Sprint Goal: QR signing, feedback, lost & found, announcements, SOS alert

🛣️  API & Route Work

- POST /api/qr/sign — generate signed QR payload for a transaction

- POST /api/qr/verify — verify QR signature on scan

- POST /api/commuter/feedback — submit ride feedback

- GET /api/lost-found + POST /api/lost-found

- PUT /api/lost-found/{id}/claim

- GET /api/announcements + POST (admin only)

- POST /api/commuter/sos — broadcast SOS alert

🔐  Auth & Security

- QR signing: HMAC-SHA256 with server secret key (never expose secret client-side)

- QR verify: reject tampered or expired QR payloads

- SOS: rate-limit to prevent abuse (max 1 per 5 minutes per commuter)

- Feedback: commuter only, linked to commuter_id

⚙️  Core System Logic

- QR Signing Flow

- Sign payload: { transaction_id, amount, commuter_id, exp } with HMAC

- Verify: recompute HMAC, reject if mismatch or expired

- QR is tied to a transaction — NOT a wallet funding source

- SOS: store alert with commuter_id, lat, lng, timestamp — admin notified via broadcast or push

- Announcements: admin creates, all commuters can read, mark-as-read per user

- Lost & Found: commuter claims item → status = claimed, admin confirms

🗃️  Database / Laravel Structure

- Migration: feedback (id, commuter_id, conductor_id?, shift_id?, rating, comment, created_at)

- Migration: lost_items (id, description, reported_by, status, claimed_by?, created_at)

- Migration: announcements (id, title, body, created_by, created_at)

- Migration: announcement_reads (user_id, announcement_id, read_at)

- Migration: sos_alerts (id, commuter_id, lat, lng, status, created_at)

📡  Real-time / GPS

- SOS alert may broadcast via Laravel Echo / Pusher to admin dashboard

- Announcements: commuters pull on login or dashboard load

🧹  Code Quality

- QR secret in .env only

- QrService: sign(), verify() — isolated, testable

- SOS rate limiter via Laravel's built-in throttle middleware

✅  Validation Checklist

- Signed QR cannot be tampered (modify payload → verify rejects it)

- Expired QR rejected after TTL

- SOS stores alert in DB with correct lat/lng

- Feedback links to correct commuter_id

- Announcement mark-as-read scoped per user

- Lost item claim changes status to claimed

WEEK 7    July 28 – August 3, 2025

Sprint Goal: API hardening, error standardization, dead code purge, wallet logic elimination

🛣️  API & Route Work

- Audit all routes: remove any 501 stubs that were never implemented

- Standardize all error responses: { success: false, message, errors: {} }

- Standardize all success responses: { success: true, data, meta }

- Add 404 catch-all for undefined API routes (return JSON, not HTML)

- Review and fix any inconsistent HTTP status codes (201 vs 200 for creates, etc.)

🔐  Auth & Security

- Audit all endpoints: confirm auth:sanctum + role middleware on every protected route

- Test CSRF protection on POST routes (Sanctum SPA config)

- Ensure no endpoint leaks data from other roles (test cross-role access systematically)

- Rotate any hardcoded secrets found in code to .env

⚙️  Core System Logic

- Wallet Logic Elimination Audit

- Search entire codebase for: wallet, balance, top_up, wallet_ledger, stored_funds

- Remove any wallet-related DB columns, tables, routes, or service methods

- Confirm GCash flow has NO internal balance side effect

- Any voucher/reward system must NOT store monetary balance

- Validate that hail radius check is ONLY in HailService — remove from any route/controller

- Confirm vehicle visibility endpoint has NO distance filter

🗃️  Database / Laravel Structure

- Run schema audit: verify no wallet_* tables exist

- Add missing indexes: vehicle_locations.vehicle_id, transactions.shift_id, hails.commuter_id

- Add DB-level constraints: shift.status ENUM, hail.status ENUM

- Review all FK relationships and add ON DELETE behavior

📡  Real-time / GPS

- GPS update endpoint: add server-side staleness check (reject GPS older than 30s via timestamp)

- Vehicles with no location update in 10 min: auto-mark as inactive in admin monitoring

🧹  Code Quality

- Remove all TODO/FIXME comments that reference wallet logic

- Remove unused imports across all service files

- Ensure every controller method is ≤30 lines — extract to service if not

- Verify no raw SQL queries — all queries through Eloquent or Query Builder

✅  Validation Checklist

- grep -r 'wallet' app/ returns zero results

- All API errors return JSON (not HTML exception pages)

- Cross-role access test matrix: all 403s where expected

- DB schema: no wallet-related tables or columns

- GPS stale data rejected correctly

- Postman collection passes all endpoint tests

WEEK 8    August 4 – August 10, 2025

Sprint Goal: Performance, query optimization, caching, and staging environment readiness

🛣️  API & Route Work

- Add pagination to: /api/admin/users, /api/conductor/transactions, /api/commuter/payments

- Add filtering to admin endpoints: ?role=, ?status=, ?date_from=, ?date_to=

- Add rate limiting: 60 req/min for general API, 5 req/min for auth endpoints

- Review and document all API contracts (route, method, request, response)

🔐  Auth & Security

- Implement token expiry: Sanctum tokens expire after 24h (configure in sanctum.php)

- Add brute-force protection on login: lockout after 5 failed attempts

- Ensure all file uploads (ID photos) are validated for type + size before storage

- Review CORS allowed_origins: must not be '*' in staging

⚙️  Core System Logic

- Hail expiry: ensure scheduler is running and expiring stale hails correctly

- Transaction idempotency: prevent duplicate transaction on double-POST (unique key or idempotency header)

- Webhook retry handling: PayMongo retries failed webhooks — ensure idempotent processing

🗃️  Database / Laravel Structure

- Add composite indexes for common query patterns

- Review N+1 query risks: use eager loading (with()) in listing endpoints

- Set up DB connection pooling for staging

- Create staging .env.staging — separate DB, PayMongo sandbox keys

📡  Real-time / GPS

- GPS polling: confirm 5s interval is sustainable at scale (estimate: 10 conductors = 2 req/s)

- Cache GET /api/vehicles/locations with 4s TTL (Redis or in-memory) to reduce DB hits

- Consider Laravel Echo + Pusher for real-time push if polling proves insufficient

🧹  Code Quality

- Run php artisan route:list — confirm all routes are intentional

- Run php artisan optimize — cache config, routes, views for staging

- Ensure all validation rules use FormRequest classes — no inline $request->validate()

✅  Validation Checklist

- Pagination works on all list endpoints

- Rate limiting returns 429 after threshold

- Login lockout after 5 failures

- N+1 queries eliminated (test with Laravel Debugbar or telescope)

- Staging environment boots and connects to separate DB

- PayMongo sandbox webhook verified in staging

WEEK 9    August 11 – August 15, 2025

Sprint Goal: Production hardening, final security audit, deployment readiness sign-off

🛣️  API & Route Work

- Final API contract freeze — no new endpoints after August 12

- Ensure all endpoints have Postman tests documented

- Confirm frontend API_BASE_URL environment variable is wired to Laravel backend

🔐  Auth & Security

- Run OWASP checklist: SQL injection (Eloquent protects — confirm no raw queries), XSS, CSRF

- Confirm Sanctum CSRF cookie is set correctly for production domain

- Review sensitive data in logs: ensure passwords, tokens, PayMongo keys never logged

- Set APP_DEBUG=false in production .env

- Set APP_ENV=production

⚙️  Core System Logic

- Final end-to-end flow tests: commuter hail → conductor accept → GCash payment → transaction confirmed

- GPS update → vehicle visible on commuter map → hail blocked at 1.5km → hail allowed at 0.5km

- Admin monitoring shows live vehicle positions

🗃️  Database / Laravel Structure

- Run all migrations on production DB (dry-run first)

- Seed production data: routes, vehicle master list, initial admin user

- Back up migration state before go-live

- Confirm DB user has minimal required permissions (not root)

📡  Real-time / GPS

- Confirm GPS polling or WebSocket is stable over 30-minute test window

- Verify vehicle_locations updates propagate to commuter map within 6s

🧹  Code Quality

- composer install --no-dev for production build

- php artisan config:cache + route:cache + view:cache

- Remove all debug routes (e.g. /api/debug/*, /api/test/*)

- Ensure error reporting goes to log file, not to API response body

✅  Validation Checklist

- Full E2E test: hail at 500m succeeds, at 1500m rejected

- GCash payment flow completes without wallet side effect

- All role-protection tests pass (commuter, conductor, admin isolation)

- No wallet logic in DB, routes, or services

- APP_DEBUG=false (no stack traces in responses)

- Production .env has real PayMongo live keys

- Backup verified before go-live

# Final Assessment

## Backend Readiness Score (Post-Sprint 9)

| Area | Status After Sprint 9 | Score |
| --- | --- | --- |
| Authentication | Sanctum + role middleware fully enforced | ✅ 10/10 |
| GPS System | Real-time upsert with staleness protection | ✅ 9/10 |
| Hail Radius (1KM) | 100% server-side Haversine enforcement | ✅ 10/10 |
| Payment (GCash QR) | PayMongo direct, webhook verified, no wallet | ✅ 9/10 |
| Role-Based Access | Middleware on all routes, cross-role tested | ✅ 10/10 |
| Wallet Removal | Zero wallet logic in DB, code, or routes | ✅ 10/10 |
| API Consistency | Standardized response format, pagination | ✅ 9/10 |
| Code Architecture | Thin controllers, service layer, no God classes | ✅ 9/10 |
| Security Hardening | Rate limiting, CSRF, OWASP basic audit | ✅ 9/10 |
| OVERALL | Production-ready backend | ✅ 95/100 |

## Risks if Sprint is Delayed

- Sprint 1 delay (auth/foundation): cascades all subsequent sprints — every sprint depends on it

- Sprint 2 delay (GPS/shifts): Sprint 3 hail logic cannot be tested without live vehicle locations

- Sprint 3 delay (hail): 1KM restriction remains frontend-only — critical security gap

- Sprint 4 delay (payments): GCash QR flow untested — payment failures at launch

- Sprint 7 delay (hardening): wallet ghost logic may ship to production — architectural contamination

- Sprint 8 delay (staging): no pre-production testing environment — production becomes first real test

## Deployment Recommendation

| Phase | Timeline | Gate |
| --- | --- | --- |
| Development | Week 1–7 (June 16 – August 3) | All sprints green |
| Staging | Week 8 (August 4–10) — separate DB, sandbox PayMongo | E2E tests pass |
| Production | August 11–15 — after Sprint 9 sign-off | Security audit done |

Production go-live is only recommended after Sprint 9 validation checklist is 100% complete. Partial deployments (e.g. going live before hail radius is backend-enforced) introduce critical security and logic gaps.

## Critical Architecture Warnings

- NEVER deploy with APP_DEBUG=true — full stack traces expose DB structure and server paths

- The frontend middleware.ts reads the chatco_session cookie role claim client-side — this is display routing only. The backend must ALWAYS re-verify the role via auth:sanctum + role middleware on every request.

- The gcash-payment.ts service has a sandbox fallback that simulates payments (isSimulated: true). Confirm PAYMONGO_CONFIG.isSandbox = false in production .env — the backend must never trust simulated payment results.

- shouldUseConductorApi() in the frontend defaults to API mode unless NEXT_PUBLIC_CONDUCTOR_API_MODE=local is set. Confirm this variable is NOT set in production (it would silently disable all conductor API calls).

- vehicle_locations must be an upsert (INSERT OR UPDATE by vehicle_id), not an append — otherwise the table grows unbounded and GET /api/vehicles/locations returns stale duplicates.

- The frontend's nearby-detector.ts correctly implements all units visible + 1KM hail gate logic, but this is UI-layer only. Sprint 3 backend must duplicate this exact logic in HailService — any divergence is a security gap.

CHATCO Backend Sprint Roadmap  —  Prepared for dev team use  |  June 2025